## Slide 1
Production-Grade Estimate
From de-risked POC to production v1 — effort, timeline, and where it goes
44.5–68
engineer-weeks of effort
16–22 wks
calendar (parallelized)
~4–5.5 mo
to a solid v1
2–3
mid/senior engineers
Effort by workstream (engineer-weeks, low – high)
Chart: 
| A Data & State | B Async & Scale | C Auth & Tenancy | D AI Quality ★ | E CI/CD & Deploy | F Infra & Ops | G Testing & QA
Low | 5 | 4 | 4.5 | 10 | 6 | 7 | 8
High (additional) | 2 | 3 | 1.5 | 5 | 4 | 4 | 4
BUILT · Already done (the hard part)
Multi-scanner orchestration · LLM analysis & RAG
Autonomous remediation (Claude Agent SDK on Bedrock)
GitHub PR creation — ~60–65% of steady-state value
PENDING · For production (mostly engineering, not R&D)
Persistence (scans are in-memory; RDS not wired)
Auth / RBAC / multi-tenancy — none today
Async worker (SQS provisioned, no consumer)
CI/CD triggers + test-gated validation + deploy
Infra hardening, observability, test coverage

## Slide 2
Rollout Plan & Scope Decisions
Front-load the production foundation so the AI core can run safely on real repos
PHASE 1
≈ 4–6 weeks
Production Foundation
Postgres data model + wire app (kill in-memory store)
Auth, RBAC, secrets management
Baseline test coverage
→ Deployable & safe for real repos
PHASE 2
≈ 4–6 weeks
Scale & Deploy
SQS worker — scans off the request path
CI/CD triggers (Actions / GitLab / Jenkins)
Network hardening, TLS, observability
→ Handles real volume, self-deploys
PHASE 3
≈ 6–8 weeks
AI Differentiation ★
Real prioritization (EPSS/KEV, exploitability)
Test-gated validation of AI fixes
Fix-quality eval harness; finish guardrails
→ Defensible, not just “AI Dependabot”
Decisions that move the estimate the most — lock these to tighten the range
1 Commercial vs OSS scanners
Snyk/SonarQube/Inspector add license + integration cost; POC already runs OSS equivalents
2 Code-only vs code + cloud
Inspector/Prowler = a second pipeline; recommend deferring posture scanning
3 Internal tool vs SaaS
Multi-tenancy drives how much of the Auth workstream you need
4 Languages in scope
Test-execution validation cost scales with each build ecosystem supported